## Sheet1
MATNR | Scope for DM | Issue | Action | MTART | In LIMS?
140388 | YES |  |  | ZRMS | NOT FOUND
148606 | ? | Incorrectly created Material codes.14 is Process Oil? | Rajesh to confirm with R&D | ZRMS | NOT FOUND
150810 | YES |  |  | ZRMS | NOT FOUND
160114 | ? | Incorrectly created Material codes.16 is Chemicals? | Rajesh to confirm with R&D | ZRMS | NOT FOUND
163305 | ? | Incorrectly created Material codes.16 is Chemicals? | Rajesh to confirm with R&D | ZRMS | NOT FOUND
179103 | ? | Incorrectly created Material codes.17 is solvent? | Rajesh to confirm with R&D | ZRMS | NOT FOUND
190092 | YES |  |  | ZRMS | NOT FOUND
191228 | YES |  |  | ZRMS | NOT FOUND
192620 | YES |  |  | ZRMS | NOT FOUND
193078 | YES |  |  | ZRMS | NOT FOUND
194580 | YES |  |  | ZRMS | NOT FOUND
196075 | YES |  |  | ZRMS | NOT FOUND
198805 | YES | Future usage : Indirect RM should be using ZRMS | Puneet to confirm | XCON | NOT FOUND
198808 | YES | Future usage : Indirect RM should be using ZRMS | Puneet to confirm | XCON | NOT FOUND
198809 | YES | Future usage : Indirect RM should be using ZRMS | Puneet to confirm | XCON | NOT FOUND
198901 | YES |  |  | ZRMS | NOT FOUND
198907 | YES |  |  | ZRMS | NOT FOUND
198909 | YES |  |  | ZRMS | NOT FOUND
600126 | YES |  |  | ZRMS | NOT FOUND
600128 | YES |  |  | ZRMS | NOT FOUND
600273 | YES |  |  | ZRMS | NOT FOUND
860115 | YES |  |  | ZRMS | NOT FOUND
860116 | YES |  |  | ZRMS | NOT FOUND
860117 | YES |  |  | ZRMS | NOT FOUND
860119 | YES |  |  | ZRMS | NOT FOUND
860120 | YES |  |  | ZRMS | NOT FOUND
860140 | YES |  |  | ZRMS | NOT FOUND
860438 | YES |  |  | ZRMS | NOT FOUND
890009 | YES |  |  | ZRMS | NOT FOUND
890064 | YES |  |  | ZRMS | NOT FOUND
890065 | YES |  |  | ZRMS | NOT FOUND
890828 | YES |  |  | ZRMS | NOT FOUND
898806 | YES | Future usage : Indirect RM should be using ZRMS | Puneet to confirm | XCON | NOT FOUND
930100 | ? | Incorrectly created Material codes.Nylon? | Rajesh to confirm with R&D | ZRMS | NOT FOUND
930101 | ? | Incorrectly created Material codes.Nylon? | Rajesh to confirm with R&D | ZRMS | NOT FOUND
938701 | ? |  | Rajesh to confirm with R&D | XCON | NOT FOUND
939703 | ? | Incorrectly created Material codes.Liner? | Rajesh to confirm with R&D | ZRMS | NOT FOUND
100162R | YES |  |  | ZRMS | NOT FOUND
1310010020I | ? | Incorrectly created Material codes. 13 is syntetic rubber. | Rajesh to confirm with R&D | ZRMS | NOT FOUND
1310018000I | NO |  |  | ZEMS | NOT FOUND
1310018110I | NO |  |  | ZEMS | NOT FOUND
1310018120I | NO |  |  | ZEMS | NOT FOUND
1310018130I | NO |  |  | ZEMS | NOT FOUND
1310018210I | NO |  |  | ZEMS | NOT FOUND
1310018220I | NO |  |  | ZEMS | NOT FOUND
1310018230I | NO |  |  | ZEMS | NOT FOUND
1310018310I | NO |  |  | ZEMS | NOT FOUND
1310018320I | NO |  |  | ZEMS | NOT FOUND
1310018330I | NO |  |  | ZEMS | NOT FOUND
1310018410I | NO |  |  | ZEMS | NOT FOUND
1310018420I | NO |  |  | ZEMS | NOT FOUND
1310018430I | NO |  |  | ZEMS | NOT FOUND
1310018510I | NO |  |  | ZEMS | NOT FOUND
1310018520I | NO |  |  | ZEMS | NOT FOUND
1310018530I | NO |  |  | ZEMS | NOT FOUND
1310018610I | NO |  |  | ZEMS | NOT FOUND
1310018620I | NO |  |  | ZEMS | NOT FOUND
1310018630I | NO |  |  | ZEMS | NOT FOUND
1310018640I | NO |  |  | ZEMS | NOT FOUND
1310018650I | NO |  |  | ZEMS | NOT FOUND
1310018660I | NO |  |  | ZEMS | NOT FOUND
1310018670I | NO |  |  | ZEMS | NOT FOUND
1310018680I | NO |  |  | ZEMS | NOT FOUND
1310018690I | NO |  |  | ZEMS | NOT FOUND
1310018710I | NO |  |  | ZEMS | NOT FOUND
150134B | YES |  |  | ZRMS | NOT FOUND
16 EXB212/6 | ? |  | Rajesh to confirm whether in scope or not | ZOTH | NOT FOUND
16 EXB250/6 | ? |  | Rajesh to confirm whether in scope or not | ZOTH | NOT FOUND
162713A | YES | Prefix not defined by business (Rubber chemical or all chemicals) | Rajesh to confirm with R&D | ZRMS | NOT FOUND
16EXB250/6 | ? | 16 is Chemicals? Change Material Group or Code. | Rajesh to confirm with R&D | ZRMS | NOT FOUND
17 EXB 219/6 | NO | No activity since 2020. | Rajesh to block. | ZOTH | NOT FOUND
17 EXB 236/4 | NO |  | Rajesh to block. | ZPRT | NOT FOUND
17 EXB 237/6 | ? | 17 is solvent? Change Material Group or Code. | Rajesh to confirm with R&D & Business | ZRMS | NOT FOUND
17 EXB 280/5 | NO | No activity since 2020. | Rajesh to block. | ZOTH | NOT FOUND
170191A | YES |  |  | ZRMS | NOT FOUND
170344A | YES |  |  | ZRMS | NOT FOUND
17EXB236/4 | ? | Incorrectly created Material codes. | Rajesh to confirm with R&D & Business | ZRMS | NOT FOUND
17EXB280/5 | ? | 17 is solvent? Change Material Group or Code. | Rajesh to confirm with R&D & Business | ZRMS | NOT FOUND
17EXR 282/4 | ? | 17 is solvent? Change Material Group or Code. | Rajesh to confirm with R&D & Business | ZRMS | NOT FOUND
17EXR 300/4 | ? | 17 is solvent? Change Material Group or Code. | Rajesh to confirm with R&D & Business | ZRMS | NOT FOUND
17EXR 330/4 | ? | 17 is solvent? Change Material Group or Code. | Rajesh to confirm with R&D & Business | ZRMS | NOT FOUND
17EXR265/4 | NO | Blocked Materials |  | ZPRT | NOT FOUND
17EXR265/4CB | NO | Blocked Materials |  | ZPRT | NOT FOUND
17EXR282/4CB | NO | Blocked Materials |  | ZPRT | NOT FOUND
17EXR330/4CB | NO | Blocked Materials |  | ZPRT | NOT FOUND
18 EXB 265/5 | ? |  | Rajesh to confirm whether in scope or not | ZOTH | NOT FOUND
18 EXB198/6 | ? |  | Rajesh to confirm whether in scope or not | ZOTH | NOT FOUND
18EXB239/6 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
18EXB265/5 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
18EXR435/6 | YES | wrong MG mapping - SAP Team | Cutover / Monthend - Vishal update to R10 | ZRMS | NOT FOUND
19 EXB 210/5 | YES |  |  | ZRMS | NOT FOUND
190393O | YES |  |  | ZRMS | NOT FOUND
190394B | YES |  |  | ZRMS | NOT FOUND
190394R | YES |  |  | ZRMS | NOT FOUND
190394V | YES |  |  | ZRMS | NOT FOUND
190394W | YES |  |  | ZRMS | NOT FOUND
190394Y | YES |  |  | ZRMS | NOT FOUND
191228A | YES |  |  | ZRMS | NOT FOUND
191228B | YES |  |  | ZRMS | NOT FOUND
193415B | YES |  |  | ZRMS | NOT FOUND
193415E | YES |  |  | ZRMS | NOT FOUND
193415G | YES |  |  | ZRMS | NOT FOUND
193415P | YES |  |  | ZRMS | NOT FOUND
193415R | YES |  |  | ZRMS | NOT FOUND
193415V | YES |  |  | ZRMS | NOT FOUND
193415W | YES |  |  | ZRMS | NOT FOUND
193415Y | YES |  |  | ZRMS | NOT FOUND
193416O | YES |  |  | ZRMS | NOT FOUND
193416Y | YES |  |  | ZRMS | NOT FOUND
195010O | YES |  |  | ZRMS | NOT FOUND
195010V | YES |  |  | ZRMS | NOT FOUND
21 EXB 210/7 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
4008 EX | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
45010 BK | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
52N5TOR | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
890003A | YES |  |  | ZRMS | NOT FOUND
890011G | YES |  |  | ZRMS | NOT FOUND
890011L | YES |  |  | ZRMS | NOT FOUND
890011O | YES |  |  | ZRMS | NOT FOUND
890011R | YES |  |  | ZRMS | NOT FOUND
890011W | YES |  |  | ZRMS | NOT FOUND
890011Y | YES |  |  | ZRMS | NOT FOUND
890066R | YES |  |  | ZRMS | NOT FOUND
890066V | YES |  |  | ZRMS | NOT FOUND
890828A | YES |  |  | ZRMS | NOT FOUND
BAB1201 | YES |  |  | ZRMS | NOT FOUND
BAB1301 | YES |  |  | ZRMS | NOT FOUND
BAB1401 | YES |  |  | ZRMS | NOT FOUND
BAB1501 | YES |  |  | ZRMS | NOT FOUND
BAB1601 | YES |  |  | ZRMS | NOT FOUND
BAB1701 | YES |  |  | ZRMS | NOT FOUND
BAB1801 | YES |  |  | ZRMS | NOT FOUND
BAB1901 | YES |  |  | ZRMS | NOT FOUND
BAB2001 | YES |  |  | ZRMS | NOT FOUND
BFB1201 | ? |  | Rajesh to confirm whether in scope or not | ZSFG | NOT FOUND
BFB1301 | ? |  | Rajesh to confirm whether in scope or not | ZSFG | NOT FOUND
BFB1401 | ? |  | Rajesh to confirm whether in scope or not | ZSFG | NOT FOUND
BFB1501 | ? |  | Rajesh to confirm whether in scope or not | ZSFG | NOT FOUND
BFB1501AN | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
BFB1601 | ? |  | Rajesh to confirm whether in scope or not | ZSFG | NOT FOUND
BL210035 | YES |  |  | ZRMS | NOT FOUND
BL240035 | YES |  |  | ZRMS | NOT FOUND
BL240049 | YES |  |  | ZRMS | NOT FOUND
BL270049 | YES |  |  | ZRMS | NOT FOUND
BL330051 | YES |  |  | ZRMS | NOT FOUND
BL356533 | YES | wrong MG mapping - SAP Team | Cutover / Monthend - Vishal update to R10 | ZRMS | NOT FOUND
BL400057 | YES |  |  | ZRMS | NOT FOUND
BLD0001 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | XCON | NOT FOUND
BLD0002 | YES |  |  | XCON | NOT FOUND
BLD0003 | YES |  |  | XCON | NOT FOUND
BLD0004 | YES |  |  | XCON | NOT FOUND
BLD0009 | YES |  |  | XCON | NOT FOUND
BLD0010 | YES |  |  | XCON | NOT FOUND
BLD0012 | YES |  |  | XCON | NOT FOUND
BLD0013 | YES |  |  | XCON | NOT FOUND
BLD0019 | YES |  |  | XCON | NOT FOUND
BLD0023 | YES |  |  | XCON | NOT FOUND
BLD0025 | YES |  |  | XCON | NOT FOUND
BLD0026 | YES |  |  | XCON | NOT FOUND
BLD0027 | YES |  |  | XCON | NOT FOUND
BLD0028 | YES |  |  | XCON | NOT FOUND
BLD0029 | YES |  |  | XCON | NOT FOUND
BLD0030 | YES |  |  | XCON | NOT FOUND
BLD0031 | YES |  |  | XCON | NOT FOUND
BLD0033 | YES |  |  | XCON | NOT FOUND
BLD0034 | YES |  |  | XCON | NOT FOUND
BLD0035 | YES |  |  | XCON | NOT FOUND
BLD0036 | YES |  |  | XCON | NOT FOUND
BLD0037 | YES |  |  | XCON | NOT FOUND
BLD0038 | YES |  |  | XCON | NOT FOUND
BLD0039 | YES |  |  | XCON | NOT FOUND
BLD0040 | YES |  |  | XCON | NOT FOUND
BLD0041 | YES |  |  | XCON | NOT FOUND
BLD0043 | YES |  |  | XCON | NOT FOUND
BLD0044 | YES |  |  | XCON | NOT FOUND
BLD0045 | YES |  |  | XCON | NOT FOUND
BLD0046 | YES |  |  | XCON | NOT FOUND
BLD0047 | YES |  |  | XCON | NOT FOUND
BLD0048 | YES |  |  | XCON | NOT FOUND
BLD0054 | YES |  |  | XCON | NOT FOUND
BLD0056 | YES |  |  | XCON | NOT FOUND
BLD0058 | YES |  |  | XCON | NOT FOUND
BLD0059 | YES |  |  | XCON | NOT FOUND
BLD0068 | YES |  |  | XCON | NOT FOUND
BLD0101 | YES |  |  | XCON | NOT FOUND
BLD0102 | YES |  |  | XCON | NOT FOUND
BLD0103 | YES |  |  | XCON | NOT FOUND
BLD0104 | YES |  |  | XCON | NOT FOUND
BLD0105 | YES |  |  | XCON | NOT FOUND
BLD0108 | YES |  |  | XCON | NOT FOUND
BLD0118 | YES |  |  | XCON | NOT FOUND
BLD0126 | YES |  |  | XCON | NOT FOUND
BLD0127 | YES |  |  | XCON | NOT FOUND
BOMB10BL | YES | wrong MG mapping - SAP Team | Cutover / Monthend - Vishal update to R10 | ZRMS | NOT FOUND
BOMC11BL | YES | wrong MG mapping - SAP Team | Cutover / Monthend - Vishal update to R10 | ZRMS | NOT FOUND
BOMK2BL | YES | wrong MG mapping - SAP Team | Cutover / Monthend - Vishal update to R10 | ZRMS | NOT FOUND
BOMN1BLD | YES | wrong MG mapping - SAP Team | Cutover / Monthend - Vishal update to R10 | ZRMS | NOT FOUND
BOMR7BL | YES | wrong MG mapping - SAP Team | Cutover / Monthend - Vishal update to R10 | ZRMS | NOT FOUND
BOMS1BL | YES | wrong MG mapping - SAP Team | Cutover / Monthend - Vishal update to R10 | ZRMS | NOT FOUND
BOMS2BL | YES | wrong MG mapping - SAP Team | Cutover / Monthend - Vishal update to R10 | ZRMS | NOT FOUND
BOMS3BL | YES | wrong MG mapping - SAP Team | Cutover / Monthend - Vishal update to R10 | ZRMS | NOT FOUND
BOMS4BL | YES | wrong MG mapping - SAP Team | Cutover / Monthend - Vishal update to R10 | ZRMS | NOT FOUND
CHEMSH1501_LTR | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
D636814 | YES | Prefix not defined by business (Nylon Fabric) | Rajesh to confirm with R&D | ZRMS | NOT FOUND
EB24661 | YES |  |  | ZRMS | NOT FOUND
EB44661 | YES |  |  | ZRMS | NOT FOUND
EB8612 | YES |  |  | ZRMS | NOT FOUND
EB8613 | YES |  |  | ZRMS | NOT FOUND
EB87870 | YES |  |  | ZRMS | NOT FOUND
ETF372 | YES |  |  | ZRMS | NOT FOUND
EX 1018 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
EX 2216 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
EX 3.00-12 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
EX 3530 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
EX 607 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
EX 608 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
EX 614 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
EX 707 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
EX1017 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
EX13X140X510 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
EX-619 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
EXC6739 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
EXP 13X165X510 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
EXP 11X290 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
EXP 13X165X510 | YES | wrong MG mapping - SAP Team | Cutover / Monthend - Vishal update to R10 | ZRMS | NOT FOUND
EXP 6.5 X 220 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
EXP13X165X510 | NO | Need to block no activity since 2020 | Rajesh to block. | ZPRT | NOT FOUND
EXP13X170 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
EXP14 X 185 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
EXP14 X 225 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
EXP14 X 240 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
HMPF1P03 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
ID0101A | YES |  |  | ZRMS | NOT FOUND
ID0123 | YES |  |  | ZRMS | NOT FOUND
ID0136 | YES |  |  | ZRMS | NOT FOUND
ID0141 | YES |  |  | ZRMS | NOT FOUND
ID0143 | YES |  |  | ZRMS | NOT FOUND
ID0146 | YES |  |  | ZRMS | NOT FOUND
ID0151 | YES |  |  | ZRMS | NOT FOUND
ID0161 | YES |  |  | ZRMS | NOT FOUND
ID8719 | YES |  |  | XCON | NOT FOUND
K80800000000I | NO |  |  | ZEMS | NOT FOUND
KMB1201 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KMB1301 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KMB1401 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KMB1402 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KMB1403 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KMB1501 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KMB1502 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KMB1503 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KMB1504 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KMB1601 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KMB1701 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KMB1702 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KMB1703 | ? |  | Rajesh to confirm whether in scope or not | ZSFG | NOT FOUND
KMB1704 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KMB1801 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KMB1901 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KMB2001 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KMI1401 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KMI1501 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KMS1201 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KMS1301 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KMS1401 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KMS1501 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KMS1601 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KMS1701 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KMS1801 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KMS1901 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KMS2001 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KS214310 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KS215270 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KS215310 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KS215340 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KS216270 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KS216310 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KS216340 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KS217310 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
KS217340 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
L22110 | YES |  |  | ZRMS | NOT FOUND
L22127A | YES |  |  | ZRMS | NOT FOUND
L23091 | YES |  |  | ZRMS | NOT FOUND
L23127 | YES |  |  | ZRMS | NOT FOUND
L23127A | YES |  |  | ZRMS | NOT FOUND
L23160 | YES |  |  | ZRMS | NOT FOUND
L24091 | YES |  |  | ZRMS | NOT FOUND
L24102 | YES |  |  | ZRMS | NOT FOUND
L24114 | YES |  |  | ZRMS | NOT FOUND
L25051 | YES |  |  | ZRMS | NOT FOUND
L25127B | YES |  |  | ZRMS | NOT FOUND
L26110 | YES |  |  | ZRMS | NOT FOUND
L29217 | YES | wrong MG mapping - SAP Team.Liners ? | Cutover / Monthend - Vishal update to R17 | XCON | NOT FOUND
L29218 | YES | wrong MG mapping - SAP Team.Liners ? | Cutover / Monthend - Vishal update to R17 | XCON | NOT FOUND
L29219 | YES | wrong MG mapping - SAP Team.Liners ? | Cutover / Monthend - Vishal update to R17 | XCON | NOT FOUND
L29221 | YES | wrong MG mapping - SAP Team.Liners ? | Cutover / Monthend - Vishal update to R17 | XCON | NOT FOUND
L2A0140 | YES |  |  | ZRMS | NOT FOUND
L30140 | YES |  |  | ZRMS | NOT FOUND
L40018 | YES |  |  | ZRMS | NOT FOUND
L40051 | YES |  |  | ZRMS | NOT FOUND
L40055 | YES |  |  | ZRMS | NOT FOUND
L40091 | YES |  |  | ZRMS | NOT FOUND
L40116 | YES |  |  | ZRMS | NOT FOUND
L40127 | YES |  |  | ZRMS | NOT FOUND
L40148 | YES |  |  | ZRMS | NOT FOUND
L40152 | YES |  |  | ZRMS | NOT FOUND
L40160 | YES |  |  | ZRMS | NOT FOUND
L50076A | YES |  |  | ZRMS | NOT FOUND
L50090 | ? | Are these Liners? Material Group Should be updated accordingly | Cutover / Monthend - update to R17 | ZRMS | NOT FOUND
L55060 | YES |  |  | ZRMS | NOT FOUND
L59201 | YES | Future usage : What will be future material Type for EU Liner | Puneet to confirm | XCON | NOT FOUND
L59233 | YES | Future usage : What will be future material Type for EU Liner | Puneet to confirm | XCON | NOT FOUND
L60031M16 | YES |  |  | ZRMS | NOT FOUND
L60033 | YES |  |  | ZRMS | NOT FOUND
L60063 | YES |  |  | ZRMS | NOT FOUND
L60076A | YES |  |  | ZRMS | NOT FOUND
L69203 | YES | Future usage : What will be future material Type for EU Liner | Puneet to confirm | XCON | NOT FOUND
L69207 | YES | Future usage : What will be future material Type for EU Liner | Puneet to confirm | XCON | NOT FOUND
L69215 | YES | Future usage : What will be future material Type for EU Liner | Puneet to confirm | XCON | NOT FOUND
L69222 | YES | Future usage : What will be future material Type for EU Liner | Puneet to confirm | XCON | NOT FOUND
L69223 | YES | Future usage : What will be future material Type for EU Liner | Puneet to confirm | XCON | NOT FOUND
L69224 | YES | Future usage : What will be future material Type for EU Liner | Puneet to confirm | XCON | NOT FOUND
L6A160 | YES |  |  | ZRMS | NOT FOUND
L6B033M30 | YES |  |  | ZRMS | NOT FOUND
L6C152 | YES |  |  | ZRMS | NOT FOUND
L7A0133D | YES |  |  | ZRMS | NOT FOUND
L7A0150 | YES |  |  | ZRMS | NOT FOUND
L7A0150D | YES |  |  | ZRMS | NOT FOUND
L82013 | YES |  |  | ZRMS | NOT FOUND
L82038 | YES |  |  | ZRMS | NOT FOUND
L82064 | YES |  |  | ZRMS | NOT FOUND
L82076 | YES |  |  | ZRMS | NOT FOUND
L82102 | YES |  |  | ZRMS | NOT FOUND
L82114 | YES |  |  | ZRMS | NOT FOUND
L82140 | YES |  |  | ZRMS | NOT FOUND
L82152 | YES |  |  | ZRMS | NOT FOUND
L84038 | YES |  |  | ZRMS | NOT FOUND
L86102 | YES |  |  | ZRMS | NOT FOUND
L99202 | YES | Future usage : What will be future material Type for EU Liner | Puneet to confirm | XCON | NOT FOUND
L99204 | YES | Future usage : What will be future material Type for EU Liner | Puneet to confirm | XCON | NOT FOUND
L99211 | YES | Future usage : What will be future material Type for EU Liner | Puneet to confirm | XCON | NOT FOUND
L99212 | YES | Future usage : What will be future material Type for EU Liner | Puneet to confirm | XCON | NOT FOUND
L99214 | YES | Future usage : What will be future material Type for EU Liner | Puneet to confirm | XCON | NOT FOUND
L99216 | YES | Future usage : What will be future material Type for EU Liner | Puneet to confirm | XCON | NOT FOUND
L99234 | YES | Future usage : What will be future material Type for EU Liner | Puneet to confirm | XCON | NOT FOUND
L99235 | YES | Future usage : What will be future material Type for EU Liner | Puneet to confirm | XCON | NOT FOUND
L9A0042M10 | YES |  |  | ZRMS | NOT FOUND
L9B6110 | YES |  |  | ZRMS | NOT FOUND
L9B6160 | YES |  |  | ZRMS | NOT FOUND
L9B6160M30 | YES |  |  | ZRMS | NOT FOUND
LB7000 | YES | Prefix not defined by business.(Lables) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
LB9777 | YES | Prefix not defined by business.(Lables) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
LB9779 | YES | Prefix not defined by business.(Lables) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
LB9781 | YES | Prefix not defined by business.(Lables) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
LB9782 | YES | Prefix not defined by business.(Lables) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
LB9783 | YES | Prefix not defined by business.(Lables) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
LB9785 | YES | Prefix not defined by business.(Lables) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
LB9786 | YES | Prefix not defined by business.(Lables) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
LB9787 | YES | Prefix not defined by business.(Lables) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
LB9788 | YES | Prefix not defined by business.(Lables) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
LB9789 | YES | Prefix not defined by business.(Lables) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
LB9790 | YES | Prefix not defined by business.(Lables) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
LB9791 | YES | Prefix not defined by business.(Lables) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
LB9792 | YES | Prefix not defined by business.(Lables) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
LB9793 | YES | Prefix not defined by business.(Lables) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
LC1310010020I | ? | Labels from APMEA typically belongs to R20 . LC - prefix also belongs to label? | Cutover / Monthend - update to R20 | ZRMS | NOT FOUND
LTB1501 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
LTB1601 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
MCRSS1801 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
MCRTB1701 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
MCRTB1901 | ? | Incorrectly created Material codes. | Rajesh to confirm with Business | ZRMS | NOT FOUND
MV20 | NO |  |  | ZSFG | NOT FOUND
MV20EX | NO |  |  | ZSFG | NOT FOUND
MV79 | NO |  |  | ZSFG | NOT FOUND
MV79-EX | NO |  |  | ZSFG | NOT FOUND
OMT879-K | NO |  |  | ZSFG | NOT FOUND
OMXK140R-K | NO |  |  | ZSFG | NOT FOUND
P1SDADHTP | NO |  |  | ZPAK | NOT FOUND
PB02230 | YES |  |  | ZRMS | NOT FOUND
PB04660 | YES |  |  | ZRMS | NOT FOUND
PB05075 | YES |  |  | ZRMS | NOT FOUND
PB05670 | YES |  |  | ZRMS | NOT FOUND
PB83044 | YES |  |  | ZRMS | NOT FOUND
PBOPPTPE | NO |  |  | ZPAK | NOT FOUND
PCDRUM25 | NO |  |  | ZPAK | NOT FOUND
PCNCARTN | NO |  |  | ZPAK | NOT FOUND
PCNPKSLP | NO |  |  | ZPAK | NOT FOUND
PESFM8256 | NO |  |  | ZPAK | NOT FOUND
PF2E18 | YES |  |  | ZRMS | NOT FOUND
PF2E20 | YES |  |  | ZRMS | NOT FOUND
PF2E25 | YES |  |  | ZRMS | NOT FOUND
PF2E32 | YES |  |  | ZRMS | NOT FOUND
PF2E42 | YES |  |  | ZRMS | NOT FOUND
PF3E36 | YES |  |  | ZRMS | NOT FOUND
PF7P260 | YES |  |  | ZRMS | NOT FOUND
PF7P268 | YES |  |  | ZRMS | NOT FOUND
PF9304 | YES |  |  | ZRMS | NOT FOUND
PF9E60 | YES |  |  | ZRMS | NOT FOUND
PFILM625 | NO |  |  | ZPAK | NOT FOUND
PFILM900 | NO |  |  | ZPAK | NOT FOUND
PPOBAG24 | NO |  |  | ZPAK | NOT FOUND
PPVCC925 | NO |  |  | ZPAK | NOT FOUND
PSWFIL12 | NO |  |  | ZPAK | NOT FOUND
PTF473 | YES | wrong MG mapping or Incorrectly created Material code | Cutover / Monthend - Vishal update to R08 | ZRMS | NOT FOUND
PUS1201 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
PUS1301 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
PUS1401 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
PUS1402 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
PUS1501 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
PUS1502 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
PUS1601 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
PUS1702 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
PUS1801 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
PUS1901 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
PUS2001 | YES | Prefix not defined by business (bladders) | Rajesh to agree on rule with Business | ZRMS | NOT FOUND
TORA16BL | YES | wrong MG mapping - SAP Team | Cutover / Monthend - Vishal update to R10 | ZRMS | NOT FOUND
TORA3NBL | ? |  | Rajesh to confirm whether in scope or not | ZSFG | NOT FOUND
TORG16EXR560BL | YES | wrong MG mapping - SAP Team | Cutover / Monthend - Vishal update to R10 | ZRMS | NOT FOUND
TORG17EXR520BL | YES | wrong MG mapping - SAP Team | Cutover / Monthend - Vishal update to R10 | ZRMS | NOT FOUND
TORG1COTHBL | YES | wrong MG mapping - SAP Team | Cutover / Monthend - Vishal update to R10 | ZRMS | NOT FOUND
TORG1THBL | YES | wrong MG mapping - SAP Team | Cutover / Monthend - Vishal update to R10 | ZRMS | NOT FOUND
TORG20EXR600 | YES | wrong MG mapping - SAP Team | Cutover / Monthend - Vishal update to R10 | ZRMS | NOT FOUND
X160215 | YES | Prefix not defined by business (Rubber chemical or all chemicals) | Rajesh to confirm with R&D | ZRMS | NOT FOUND
X162213 | YES | Prefix not defined by business (Rubber chemical or all chemicals) | Rajesh to confirm with R&D | ZRMS | NOT FOUND
X191111 | YES |  |  | ZRMS | NOT FOUND
X194580 | YES |  |  | ZRMS | NOT FOUND
X195411 | YES |  |  | ZRMS | NOT FOUND
X600434 | YES |  |  | ZRMS | NOT FOUND